Status & blockers — Manco Capture Agent (Sprint 1)

Status as of 25 June 2026

Project: Manco Capture Agent — emails to Jira Tasks on the Manco Board (VFST2), with human approval in Teams.

Build pack: https://github.com/snerantie/Copilot-Studio/tree/feat/manco-capture-sprint1/manco-capture

# 1. Headline

Sprint 1 is approximately 60% built.

Foundations (Teams channel, SharePoint list, Jira token, Outlook trigger) are DONE.

Two blockers prevent completion of the AI extraction step. Both are Microsoft licensing / policy decisions, not technical problems.

# 2. Progress checklist

## Phase 1 — Provisioning

| # | Task | Status |
| --- | --- | --- |
| 1.1 | Capture – Approvals private Teams channel inside the Manco Team | DONE |
| 1.2 | Capture Audit SharePoint list in the Manco SharePoint site | DONE |
| 1.3 | Jira Cloud API token created and stored | DONE |
| 1.4 | Outlook category "Capture" created on user mailbox | DONE |
| 1.5 | AI Builder access — Models available, Prompts disabled | PARTIAL |

## Phase 2 — Power Platform environment variables

| # | Task | Status |
| --- | --- | --- |
| 2.1 | manco_JiraBaseUrl (Text) | Pending |
| 2.2 | manco_JiraAuthEmail (Text) | Pending |
| 2.3 | manco_JiraApiToken (Secret) | Pending |

## Phase 3 — Copilot Studio extraction agent

| # | Task | Status |
| --- | --- | --- |
| 3.1 | Create agent Manco Capture | DONE |
| 3.2 | Define extraction prompt (text content) | DONE |
| 3.3 | Wire as callable Tool with structured inputs/outputs | BLOCKED — Tools needs upgrade |
| 3.4 | Fallback: wire as Topic with workaround | In progress |

## Phases 4–6

| Phase | Task | Status |
| --- | --- | --- |
| 4 | Build Power Automate parent flow (Outlook → extract → dispatch) | Pending — depends on Phase 3 |
| 5 | Build Power Automate approval flow (card → Jira → audit) | Pending — depends on Phase 4 |
| 6 | End-to-end testing (5-scenario plan) | Pending |

# 3. Blockers in detail

## Blocker A — Copilot Studio "Tools / Knowledge / Agents" require upgrade

What I see: the left navigation of my Copilot Studio agent shows Knowledge (needs upgrade), Tools (needs upgrade), Agents (needs upgrade). Only Topics is available without upgrade.

Impact: I cannot use the textbook architecture (Tool exposing LLM extraction with structured inputs/outputs callable by Power Automate). I can work around with Topics, but it's less clean and constrains the next two sprints heavily.

Action needed: approve the Microsoft Copilot Studio capability upgrade. See business-case-upgrade for the full justification.

## Blocker B — AI Builder Prompts disabled by admin policy

What I see: in make.powerautomate.com → AI hub, the Prompts feature shows "This feature has been disabled. Prompts have been disabled. Please contact your administrator."

Impact: I cannot use AI Builder Prompts as the LLM provider for the Power Automate flow. Workaround tested and working: route the prompt through Copilot Studio instead.

Action needed: ask the Power Platform admin whether Prompts can be enabled under existing governance.

Suggested message to the admin:

"We're building an AI agent for the Manco Board on Copilot Studio. The Power Automate flow needs to invoke a generative AI prompt. AI Builder Prompts is currently disabled in our tenant. Can it be enabled for the [environment name] environment under existing governance, or what is the approved path? Happy to align with the standard."

# 4. Workaround being tested

In Copilot Studio's basic tier we can still:

Build the agent and a Topic.

Use the Prompt node inside the Topic (validated in a throwaway test agent).

Invoke the Topic from Power Automate via the Microsoft Copilot Studio connector.

Caveats:

More glue code in Power Automate.

Harder to monitor and govern the LLM call.

Sprint 2 (Reporter) is doable on the same workaround but inelegant.

Sprint 3 (Insights) is effectively blocked without Knowledge.

# 5. What I need from my manager

| # | Decision | Default if no decision |
| --- | --- | --- |
| 1 | Approve Copilot Studio capability upgrade | Sprint 1 continues on workaround; Sprints 2 and 3 deferred |
| 2 | Approve raising AI Builder Prompts policy with admin | Sprint 1 continues via Copilot Studio workaround |
| 3 | Continue Sprint 1 on workaround in parallel? | Yes — pause now would lose momentum |
| 4 | Confirm M365 Copilot licence status for me + my manager | Unknown — useful to confirm |

# 6. Suggested next steps

1.  Now (no decision needed): finish Phase 2 — store Jira credentials as Power Platform environment variables. Independent of the LLM path.

2.  Now (no decision needed): continue exploring the Topics-paradigm workaround for Phase 3.

3.  This week: manager review of the business case and decision on the upgrade.

4.  This week: approach the Power Platform admin re: AI Builder Prompts policy (parallel track).

5.  Once upgrade is approved: migrate Phase 3 from Topics workaround to Tools paradigm. ~30 minutes of rework — no other phase affected.

# 7. Reference

Build pack: https://github.com/snerantie/Copilot-Studio/tree/feat/manco-capture-sprint1/manco-capture

Open pull request: https://github.com/snerantie/Copilot-Studio/pull/1

Business case for upgrade: business-case-upgrade.docx (this document's sibling)